# ECOLM Review Project

Chris Cannam, Particular Programs Ltd  
Project with Tim Crawford and David Lewis, Goldsmiths  
May – July 2023

## Aim

Review the ECOLM (Electronic Corpus of Lute Music) and related music resources, and produce a report and recommendations for a low-cost sustainability plan with scope for incremental improvement using datasets from several other possible contributors.

## Work Units and Costings

|  |  |  |  |
| --- | --- | --- | --- |
|  | Work | Proportion of whole | Cost ex VAT |
| 1 | Research – Review project background and musicological context. Identify and interview model users of resources of this type and document findings. | 30% | £1248 |
| 2 | Analyse – Carry out technical review of ECOLM and related datasets. Evaluate technical status in light of developments in good practice for data and metadata management. | 30% | £1248 |
| 3 | Report – Write up findings. Propose one or more potential paths to sustainable future development and assess their viability. | 40% | £1664 |